## Sheet1
Project Title
Project Location (Town & Country) |  |  |  | Project Number
As at:
Project Schedule (SAMPLE) |  |  | 2007-08-30
Phases |  | From | To | Duration
Planning
ToR for Project Manager (PM) |  | 2007-01-02 | 2007-01-05 | 4
Select & Hire Project Manager |  | 2007-01-08 | 2007-01-26 | 19
Planning Package | Gather information | 2007-02-05 | 2007-02-23 | 19
| Write Scope | 2007-02-26 | 2007-03-09 | 12
| Prepare Budget Estimate | 2007-02-26 | 2007-03-09 | 12
| Project Scope of Work (SoW) | 2007-02-26 | 2007-03-09 | 12
Design (A/E) Procurement | Prepare Design SoW (RFP) | 2007-03-12 | 2007-03-17 | 6
| Prepare Design Fee Estimate | 2007-03-12 | 2007-03-17 | 6
| Competitive Procurement | 2007-03-20 | 2007-04-06 | 18
| Negotiate Scope & Fee | 2007-04-09 | 2007-04-11 | 3
| Award Design Contract | 2007-04-12 | 2007-04-20 | 9
|  | TOTAL PLANNING PHASE |  | 108
Design
Pre-Design | Meeting | 2007-04-23 | 2007-04-23 | 1
| Minutes of the Meeting | 2007-04-24 | 2007-04-27 | 4
Concept Design | Submittal Preparation and Delivery | 2007-04-24 | 2007-05-07 | 14
| Concept Design Review and comments delivery | 2007-05-08 | 2007-05-11 | 4
| Deliver consolidated comments to A/E | 2007-05-14 | 2007-05-16 | 3
35% Design Submittal | Submittal Preparation and Delivery | 2007-05-17 | 2007-07-13 | 58
| Review | 2007-07-16 | 2007-07-27 | 12
| Consolidated comments to A/E | 2007-07-30 | 2007-08-03 | 5
| Review Meeting | 2007-08-08 | 2007-08-09 | 2
| Minutes of the Meeting | 2007-08-10 | 2007-08-20 | 11
100% Design Submittal | Submittal Preparation and Delivery | 2007-08-10 | 2007-09-17 | 39
| Review | 2007-09-18 | 2007-09-21 | 4
| Consolidated comments to A/E | 2007-09-24 | 2007-09-25 | 2
| Review Meeting | 2007-10-03 | 2007-10-04 | 2
| Minutes of the Meeting | 2007-10-05 | 2007-10-12 | 8
Final Design Submittal | Submittal Preparation and Delivery | 2007-10-05 | 2007-10-29 | 25
| Backcheck & Approval | 2007-10-30 | 2007-11-16 | 18
|  | TOTAL DESIGN PHASE |  | 158
Construction Permit Application (*)
| Application to local authorities | Permits shall be requested as soon as possible, depending on local requirements for design items to be submitted. The time requirement for construction permit approval may be largely differemt, depending on the country. Moreover, while in the most countries permits must be released prior to the star of construction work, it is possible that, depending on local regulations or specific agreements with the local government, the construction work starts prior to the release of permits.
Permits approved
TOTAL CONSTRUCTION PROCUREMENT PHASE
Construction Procurement (Tender)
| RFP Advertisement | 2008-01-11 | 2008-01-24 | 14
| Pre-Bid Conference | 2007-12-05 | 2007-12-05 | 1
| Proposals Preparation | 2007-12-01 | 2008-02-29 | 91
| Proposals Opening | 2008-03-01 | 2008-03-03 | 3
| Proposals Evaluation | 2008-03-04 | 2008-03-11 | 8
| Technical Panel's Report | 2008-03-12 | 2008-03-17 | 6
| Tender Approval | 2008-03-18 | 2008-03-27 | 10
| Contract Award | 2008-03-31 | 2008-04-06 | 7
|  | TOTAL CONSTRUCTION PROCUREMENT PHASE |  | 86
Construction
| Mobilization & Site Preparation | 2008-04-09 | 2008-04-22 | 14
| Pre-Construction Submittals | 2008-04-09 | 2008-04-22 | 14
| Pre-Construction Conference | 2008-04-24 | 2008-04-25 | 2
| Notice to Proceed Construction | 2008-04-28 | 2008-04-28 | 1
| Construction (detailed schedule attached) | 2008-04-28 | 2008-10-09 | 165
| Testing & Commissioning | 2008-10-13 | 2008-10-30 | 18
|  | TOTAL CONSTRUCTION PHASE |  | 204
Occupancy
| Move | 2008-11-03 | 2008-11-18 | 16
|  | TOTAL OCCUPANCY PHASE |  | 16
| TOTAL DURATION | 2007-01-02 | 2008-11-18 | 686
Formulas:
To = [From]+[Duration]-1